## Sheet1
Task | Low (hours) | High (hours) | Avg (hours) | Notes
General Tasks and Infrastructure
Inspect legacy assets for grey bar ad from creative team to determine adaptability and reuse | 1 | 3 | 2
Prototype of presentation and approach for mobile ads in showcase | 4 | 12 | 8 | Will impact user experience design being prepared by other resources
Top Position (fixed) Bar Ad
Determine reusability of legacy assets for creation of layout framework | 0.5 | 1 | 0.75
Implement HTML/CSS structure for visual framework | 2 | 4 | 3
Implement and test template comprised of visual framework and attached behaviors | 1 | 1.5 | 1.25
Translate test template into Admin Portal Sample Ad template format | 0.5 | 1 | 0.75
Create Admin Portal custom Ad Unit Size to represent the new Sample Ad template | 0.25 | 0.5 | 0.375
Unit Testing | 0.5 | 1 | 0.75
Bottom Position (fixed) Bar Ad
Determine reusability of legacy assets for creation of layout framework | 0.5 | 1 | 0.75
Implement HTML/CSS structure for visual framework | 1 | 2 | 1.5
Implement and test template comprised of visual framework and attached behaviors | 0.5 | 1 | 0.75
Translate test template into Admin Portal Sample Ad template format | 0.5 | 1 | 0.75
Create Admin Portal custom Ad Unit Size to represent the new Sample Ad template | 0.25 | 0.5 | 0.375
Unit Testing | 0.5 | 1 | 0.75
Center Position (fixed) Bar Ad
Determine reusability of legacy assets for creation of layout framework | 0.5 | 1 | 0.75
Implement HTML/CSS structure for visual framework | 2 | 6 | 4
Implement and test template comprised of visual framework and attached behaviors | 2 | 3 | 2.5
Translate test template into Admin Portal Sample Ad template format | 0.5 | 1 | 0.75
Create Admin Portal custom Ad Unit Size to represent the new Sample Ad template | 0.25 | 0.5 | 0.375
Unit Testing | 0.5 | 1 | 0.75
Showcase Prototype Templates
Full Screen Standard Sample | 1 | 2.5 | 1.75
Full Screen Standard Sample with Different Horizontal/Vertical Assets | 1 | 2.5 | 1.75
Full Screen Click-Through Sample | 1 | 2.5 | 1.75
Full Screen Click-Through Samplek with Different Horizontal/Vertical Assets | 1 | 2.5 | 1.75
320x50 Bottom Position Mobile Sample | 1 | 2.5 | 1.75
728x90 Center Position Mobile Sample | 1 | 2.5 | 1.75
728x90 Center Position Mobile Sample | 1 | 2.5 | 1.75
300x250 Center Position Mobile Sample | 1 | 2.5 | 1.75
300x250 Center Position Mobile Sample | 1 | 2.5 | 1.75
Unit Testing | 1 | 2.5 | 1.75
Totals (hours) | 28.75 | 68 | 48.375
Assumptions:
This estimate is considered a high-level estimate with a +/- 50% degree of inaccuracy due to unknowns within the requirements.
The top and bottom position fixed ads (lines 6 and 13) can share a majority of code and styling. When one is complete, it should greatly lessen the time needed for the other. In this estimate, it is assumed that the top position ad is complete and available for reuse when beginning development on the bottom ad.
These assets will be created with dummy placeholder creative assets. When the final requirements and creative assets for the showcase are known, they will need to be updated.
The target device profiles are: iPhone (iOS 5/6), iPhone Retina (iOS 5/6), iPad (iOS 5/6), iPad Retina (iOS 5/6), Android v2.3 (Gingerbread), Android v4.0 (Ice Cream Sandwich), Android v4.2 (Jelly Bean)
Risks:
There are areas of requirements that remain unknown. As these are considered and details become available, they may have an imact on the estimated LOE.
There are no creative assets currently available. Placeholders will be used in the interim, but additional time will be required to integrate the actual assets when they become available.
The development team does not currently have hardware available to test the following device profiles: iPad Retina (iOS 5/6), Android v2.3 (Gingerbread), Android v4.2 (Jelly Bean)